## Weekly Progress
Bachelor Thesis - Weekly Progress Tracker
Inside the Battery: Entschluesselung von Batteriedaten ueber den CAN-Bus
Week | Date Range | Phase | What I Did | Deliverables / Output | Status
Week 1 | 03.03 - 08.03.2026 | Setup & First Analysis | - Got the MF4 files from the CANedge2 loaded into Python - Wrote mf4_reader.py to parse all 4 log files into a single DataFrame - Built reverse_engineer.py with 9 different analysis techniques (byte time series, bit heatmaps, boundary detection, 16-bit testing, counter/checksum detection, ASCII detection, scaling analysis, per-source comparison) - Ran the full analysis pipeline on all 7 CAN IDs (0x065 - 0x06F) - Wrote can_decoder.py with signal definitions for confirmed signals - Tried UDS PID matching - found 145 battery PIDs available but they use 29-bit CAN IDs (UDS diagnostic) vs our 11-bit passive data - Created full documentation of all findings - Generated 39 RE plots + 8 decoded plots - Exported merged CAN data as CSV - Reorganised folder structure (src/, data/, output/, docs/) | mf4_reader.py, reverse_engineer.py, can_decoder.py, uds_decoder.py, analyze_patterns.py 39 plots in output/plots/ DOCUMENTATION.md (full analysis) output/can_data.csv | Done
Week 2 | 09.03 - 15.03.2026 | Tools & Organisation | - Built a full CAN Analyzer GUI in Python (PyQt5 + pyqtgraph) 6 tabs: Sniffer, ID Analysis, Signal Plotter, Payload Analysis, Flow Analysis, Hex Matrix - Python GUI too slow -> built native CAN Analyzer v2 in Rust (egui) 4 tabs: Data Flow, Sniffer, Signal Plotter, Stats - Data Flow tab: real-time hex matrix with byte-change highlighting - Added direct MF4 loading to the Rust app - Created organisation documents (weekly tracker, thesis plan, project overview) - Refocused thesis on BATTERY parameters per lecturer feedback - Created data collection strategy document - Created data collection procedure template | src/can_analyzer.py (Python GUI) can_analyzer/ (Rust app, can-analyzer.exe) Weekly_Progress.xlsx Thesis_Plan_and_Methodology.md Data_Collection_Strategy.md Data_Collection_Procedure.md | Done
Week 3 | 16.03 - 22.03.2026 | Data Collection | - Check CANedge2 capabilities: can it send 29-bit extended CAN frames? - Test UDS request via CANedge2 transmit list (Strategy A): send SOC request (03 22 02 8C) to BMS at 0x17FC007B - Check if BMS responds (look for 0x17FE007B in logs) - If no response: check diagnostic session setup (0x10 0x03) - If CANedge2 can't transmit: evaluate Strategy B (external OBD adapter + CANedge2 as passive logger) - First battery data recording (standstill baseline) - Re-examine existing data with battery lens: are 0x066/0x067 temperatures actually battery temps? - Try recording during driving for battery current/voltage changes | Strategy validation: which approach works First battery data (SOC, voltage, current) Updated CANedge2 config Session logs with annotations | In Progress
Week 4 | 23.03 - 29.03.2026 | Battery Data Collection | - Full battery data collection using validated strategy - Scenario 1: Standstill baseline (5 min, all battery params stable) - Scenario 2: Constant speed driving (50, 100 km/h) -> observe battery current/voltage under steady load - Scenario 3: Acceleration & regen braking -> peak current, regen current direction change - Scenario 4: Extended drive (20-30 min) for SOC decrease tracking - If possible: configure cell voltage requests (ISO-TP needed) - Manual annotation for every test with timestamps | Battery recordings (4+ scenarios) Annotation logs Initial UDS response decoding | Planned
Week 5 | 30.03 - 05.04.2026 | Battery Data Collection 2 | - Charging session recording (DC fast charge if available) -> SOC increase, charging current, battery temp rise - Cold start recording (after overnight park) -> low battery temp, PTC heater activity, power limits - Temperature under load (mixed driving, watch temp sensors) - If cell voltages accessible: record cell voltage spread - Start writing: CAN bus + UDS theory chapter - Start writing: battery fundamentals section | Charging + cold start recordings Draft: Theoretical background (~5 pages) | Planned
Week 6 | 06.04 - 12.04.2026 | Battery Analysis | - Decode all captured UDS battery responses - SOC: validate against dashboard reading - Voltage: check if pack voltage matches expected range (~350-410V) - Current: verify direction (negative=discharge, positive=charge) - Temperature: compare with ambient temp, check heating behaviour - Cross-correlate: battery current vs driving speed - Map out which PIDs responded and which didn't - Write CANedge2 implementation chapter | Decoded battery parameter table Validation against dashboard readings Draft: CANedge2 + Implementation (~5 pages) | Planned
Week 7 | 13.04 - 19.04.2026 | Deep Analysis | - Cell voltage analysis (if data available): voltage spread, weakest cell, balancing behaviour - Temperature distribution across 18 sensor points - Battery behaviour comparison: driving vs charging vs idle - Power calculation: P = V * I from decoded voltage and current - Energy consumption analysis: kWh over distance - Build partial DBC file with confirmed battery signals - Re-examine passive CAN data (0x065-0x06F) for any battery signals | Cell voltage analysis plots Temperature distribution maps vw_id_buzz_battery.dbc (partial) | Planned
Week 8 | 20.04 - 26.04.2026 | Writing | - Write methodology chapter: data collection strategy, why UDS was needed, 9 RE techniques for passive data, controlled test scenarios - Write analysis chapter (first half): passive CAN analysis of 0x065-0x06F, UDS battery parameter decoding approach | Draft: Methodology (~8 pages) Draft: Analysis part 1 (~5 pages) | Planned
Week 9 | 27.04 - 03.05.2026 | Writing | - Write analysis chapter (second half): battery parameter results, SOC/voltage/current/temp cell voltage analysis, charging vs driving comparison - Create publication-quality figures (300 DPI) consistent style across all battery data plots - Write results chapter: what was decoded and how confident | Draft: Analysis part 2 + Results (~10 pages) All final figures | Planned
Week 10 | 04.05 - 10.05.2026 | Validation | - Validation data collection: new recordings specifically to verify - Compare decoded SOC vs dashboard SOC (% error) - Compare decoded temperature vs external thermometer - Check voltage plausibility (expected ~3.6-4.2V per cell, ~350-410V pack) - Compute error metrics: MAE, R-squared, max deviation - Document validation results with evidence | Validation dataset Error metrics report Validation results section | Planned
Week 11 | 11.05 - 17.05.2026 | Writing | - Write discussion chapter: limitations (gateway filtering, CAN bus access, ISO-TP), comparison with other approaches (PASTA, comma.ai opendbc), implications for EV battery research, ethical/security considerations - Write conclusion and future work - Write abstract (English + German) | Draft: Discussion + Conclusion (~8 pages) Abstract | Planned
Week 12 | 18.05 - 24.05.2026 | Finalisation | - Full read-through and proofreading - Check all references and bibliography - Appendix: code listings, DBC file, raw data samples, UDS PID reference table, all analysis plots - PDF formatting, page numbers, margins - Final review, print, submit | Final thesis document (45-60 pages) Complete code repository Partial DBC file (battery signals) | Planned
Legend: | Done | In Progress | Planned

## Signal Tracking
CAN Signal Tracking
CAN ID | Byte(s) | Signal Name | Status | Confidence | Scaling | Unit | Validated?
0x065 | B[0] | NM_STATE | Decoded | HIGH | enum | - | Need more wake cycles
0x066 | B[0] | OperatingMode | Decoded | HIGH | enum (0x01/0x03) | - | Partial
0x066 | B[1:2] | MsgCounter | Decoded | HIGH | 1:1 (big-endian) | count | Yes, wrapping OK
0x066 | B[3] | Temperature_A | Decoded | MEDIUM | raw - 40 | deg C | Need thermometer
0x066 | B[4:5] | ASCII Marker 'T-' | Decoded | HIGH | ASCII | - | Yes
0x067 | B[0] | Dynamic_A | Partial | LOW | unknown | ? | Need controlled scenarios
0x067 | B[1] | Temperature_B | Partial | MEDIUM | unknown | deg C? | Need validation
0x067 | B[3] | Multiplexer | Decoded | MEDIUM | 3-bit enum | - | Need more states
0x067 | B[5] | Temperature_C | Decoded | MEDIUM | raw - 40 | deg C | Cross-validated w/ 0x066
0x068 | B[0] | Signal_D | Partial | LOW | unknown | ? | Need scenarios
0x068 | B[3] | StatusFlag | Decoded | HIGH | binary 0/1 | - | Yes
0x06A | ALL | EventMsg | Unknown | LOW | - | - | Only 126 msgs, need more data
0x06B | B[0:3] | Signals F-H | Partial | LOW | unknown | ? | Need scenarios
0x06F | B[0:7] | 8 independent signals | Partial | LOW | unknown | ? | NOT encrypted (proved)
Legend: | Decoded | Partial | Unknown

## Tools and Software
Tools & Software Used
Tool / Software | Version | Purpose | Status
Python | 3.13 | Main scripting language for analysis | Installed
asammdf | 7.x | Reading MF4 (ASAM MDF4) log files | Installed
pandas | 2.x | Data manipulation and DataFrame handling | Installed
numpy | 1.24+ | Numerical operations, array processing | Installed
matplotlib | 3.7+ | Plotting and figure generation | Installed
PyQt5 | 5.15+ | Python GUI framework (CAN Analyzer v1) | Installed
pyqtgraph | 0.13+ | Fast interactive plots in Python GUI | Installed
Rust | 1.94 | Native CAN Analyzer v2 (fast, compiled) | Installed
eframe / egui | 0.31 | Rust GUI framework (immediate mode) | Installed
egui_plot | 0.31 | Interactive plotting in Rust app | Installed
CANedge2 | Hardware | CAN bus data logger (SD card, WiFi) | Available
asammdf GUI | 8.2.5 | Visual MF4 file inspection (portable) | Available
GPS Logger App | TBD | Speed ground truth for validation | Need to install
External Thermometer | Hardware | Temperature signal validation | Need to get
LaTeX / Word | TBD | Thesis document writing | Need to set up

## Data Overview
CAN Data Overview
Current Data (Initial Recording)
Property | Value
Vehicle | Volkswagen ID Buzz (MEB platform)
Logger | CANedge2 data logger
Data Format | MF4 (ASAM MDF v4.11)
Log Files | 4 sessions (00000002 - 00000005)
Total Frames | 9,146 CAN frames
Total Duration | ~333 seconds (~5.5 minutes)
Unique CAN IDs | 7 (0x065, 0x066, 0x067, 0x068, 0x06A, 0x06B, 0x06F)
Bus Channel | Channel 9
Direction | 0 (received)
Bit Rate | 500 kbps (standard VW)
Per-CAN-ID Breakdown
CAN ID | Messages | DLC | Frequency | Present In
0x06F | 3,034 | 8 | ~9 Hz | All sources
0x065 | 3,002 | 1 | ~9 Hz | All sources
0x066 | 920 | 6 | ~5 Hz | 00000004 only
0x067 | 688 | 8 | ~4.5 Hz | 00000004 only
0x068 | 688 | 4 | ~4.5 Hz | 00000004 only
0x06B | 688 | 5 | ~4.5 Hz | 00000004 only
0x06A | 126 | varies | sporadic | 00000004 only